VOLUNTEERS DETAILED REQUIREMENTS FOR AITA

PRE-SHOW: JANUARY – FEBRUARY – MARCH – APRIL – MAY

PUBLICITY (at least 19 people for physical work and all participants for social media)

- February & March – Contact other art associations to promote your participation in AITA

- Jan – ASAP -- Send in your images to A4 Web Site for inclusion in promotion materials

- April 4nd -- Pick up Promotional Materials at Participants Meeting

- April & May – promote through individual members’ social media contacts

  - Early April – a primer “look ahead”

  - Followed by details and images

- Month of April -- Spread Post Cards around town, shows, bulletin boards, during early April, the month prior to show. Restock as necessary.

- Last weekend in April – Put out Road Signs two weeks before show

- First of May – promote through your personal social media contacts

- Post AITA Show -- Sunday night or Monday morning -- Pick up Road Signs when the show closes,

  - Pick up Road Signs on Sunday night or before 10 am Monday morning

  - If possible, chase down lost signs

- Post AITA Show plus one week

  - Return “cleaned” Materials to Publicity Director

  - Return Location Suggestion Sheet to help with next years planning. Please record observations that you think will be helpful for next years publicity work

MAY 07/25 – THURSDAY (BEFORE THE SHOW) – SHOW PREPARATION

Board Preparation Team: 6-8 people required

- Check condition of boards

- Make required repairs to boards

- Lay out drop cloths prior to painting

- Touch up scuffs and marks on boards with white paint

- Carry painted boards into the kitchen once dry

- Clean up Auditorium (drop cloths and sweep)

Lighting Team:  Lowering the Lighting: Total of 8 people required

- 2 people required to assist in the movement of the Scissor Jack and stabilizing it.

- 6 people required to assist with lowering the light booms (Requires some physical strength and gloves to hold ropes and provide assistance to town employee)

- Remove some lights from 4 booms to put on the 5th boom

- Raise the 5th boom and plug it in.

MAY 08/25 – FRIDAY – VENUE PREPARATION (Before exhibitors enter the area)

Show  Setup Team:  Chair Removal:  8-10 people

- Remove chairs from the Auditorium floor to the stage; then board setup begins.

Show Setup Team:  Table Preparation: 4-8 people

- Pull out tables required for Table artists.  Do not set up yet; leave at appropriate places for table artists and 4A table

- Set up tables after the boards have been erected.

Show  Setup Team:  Preparing the walls and raising the boards:  8-10 people

- Setting up the boards (requires the ability to get down on the floor to work for part of the time)

- Lay out boards on the floor of the auditorium

- Slide the poles into board brackets, top and bottom

- Slide the pipe connectors onto the poles

- For each row, measure the distance from the bottom of the foot to the u/s of the board using

- Laurel’s measurement tool.

- Raise the boards; tighten the connectors once in angled place (Does not require a lot of

- strength but some physical strength is required)

- Continue for the 4 rows of boards

Artist Participants:

- Once the boards are up; and only then; artists may bring their work into the hall and begin to set up their own space.

- Pick up chains and S-hooks, as required

- Note: one person to check on all chains to ensure they are all clipped on properly

Venue Decorating Team:  3-4 people plus one person with a car (SUV or Van)

- Decorating team; hang or place indoor signs (after 4:30)

- Add the lighting to the signage indoors

- Decorate the main stair - if we are doing something there.

- Set up 4A table

- Person with car: Pick up and place Large street and Directional signs in downtown Almonte

MAY 10/25 – SUNDAY – SHOW TEAR DOWN

Artist Participants:

- All Artists must wait to Show Closing Time before packing up

- Please return chains and S-hooks to the 4A tubs

- Artists to pack up and remove boxes from the hall to their cars.

- All those working on tear-down, return to the hall.

Show Teardown Team:  Tearing Down Boards: 8 – 10 people

- Loosen connectors on boards one row at a time

- Lay one row onto the floor

- Remove poles

- Stack boards onto the rack

- Continue for the next 3 rows.

Show Teardown Team:  Tables & Chairs: 2 – 3 people

- Once space is available and access to storage drawers is available, put away all tables first

- Clean up hall

- When space is available, remove chairs from stage and stack along wall

- At the end, help to transport supplies to A4 vehicles

Lighting Team:  Raise the lights (assistance to town employee): 8 people required

- Physical strength and gloves needed to work with the ropes to keep the boom level while raising and lowering)

- Drop the Centre boom

- Remove the lights from it

- Relocate and raise this boom

- Using the ropes raise the lights and hold while town employee secures them in place

- Continue for the remaining 3 booms

Venue Decorating Team:   Remove & Store Venue Decoration: 3-4 people

- Decorating team remove all outdoor and indoor signage and for storage

- Return lighting to 4A box

- 4A Table - Remove table cloths and Display Items

- Return all to 4A box

- Give all Ballots to Laurette

Street Direction Signs: 1 person with a car

- Remove large street and directional signs in Almonte

- Return to storage shed (Sunday night)

POST SHOW -- All Artists in Publicity Team: approximately 19 people

- Sunday night or Monday morning before 10 am

  - Remove all Road Signs

- During the following week

  - Clean all signs (please remove cobwebs and grass cuttings)

  - Write down what signs were lost

  - Write down what worked well and your suggestions for following year

- The following Thursday – May 14, 2025 – 4 to 6 pm at Equator Coffee

  - Return signs and report to Publicity Director

  - If you cannot make it, phone or text Laurette at 613-807-4715 to reschedule